## Corporate Risk Register
Corporate Risk Register
Risk Level | Risk ref. | Date raised | Risk Group | Site | Risk | Description | Likelihood | Impact | RAG Status & Trend | Risk Owner | Controls and Mitigating Actions | Likelihood after mitigating action | Impact after mitigating action | RAG ratings post mitigating actions | Status | Comments
| 5 | 2012-06-27 | Future DH |  | 2013-03-08 | [RESOURCES RISK CARRIED OVER FROM PROGRAMME TRANSITION RISK REGISTER - FAY TO UPDATE] Lack of resources in all the Future DH workstreams and the programme itself is affecting ability to deliver, this is particularly prevalent within the following area of work: - Insufficient dedicated resource available within the Digital team to oversee and deliver the project. A project planner plus a dedicated Project Bank (or other) resource is urgently required | 3 | 4 | A | Claire Pacey |  |  | 1. Resource levels for the Future DH projects is managed locally by the Project Leads. They will need to highlight in their Business Planning return, where further resources are required to undertake the Projects during the 13/14 financial year. Completed 2. The Future DH Programme Manager is currently seeking approval for 2 new posts (Project Manager and Planner) for the Central team to support the Future DH Programme delivery. 3. The Central team are currently identifying a project management resource to support the Digital Strategy project. |  | Open
| 21 |  | Our DH |  |  | There is a risk that potential outcomes cannot be delivered and limited benefit realisation takes place due the lack of resources available to the programme. . |  |  | A
| 22 |  | Our DH |  |  | Potential that the goodwill from across the department in terms of funding for this programme will reduce and could lead to lack of benefits realisation. |  |  | A
| 23 |  | Our DH |  |  | Potential that the Corporate IT infrastructure maybe be unable to support the delivery of the project remit resulting in limiting staff engagement via a virtual community of practice. The Hub was used previously, but since this has closed there is no-where for staff with interests in Health and Wellbeing to make contact virtually |  |  | A
|  |  | Our DH |  |  | The Central Procurement team want to move into a more customer focused model, whereby the team retain the necessary assurance and control methodology, but without it being too onerous and time consuming for the end user. In addition the team are aware that directorates use their own local practices, while some of these are productive and examples of good practice, some of the methods are weak and should be removed from the Procurement process.
| 24 |  | Our DH |  |  | Lack of Project Management Resources within the project may result in delay to delivery date and increase risk in the Departments ability to provide Ministerial System Wide Assurance. |  |  | A
| 25 |  | Our DH |  |  | The Assurance Framework and Reporting system may not be delivered as a result of a breakdown in stakeholder engagement, due to the intention being misconstrued as a means to control the Health and Social Care System from the centre. |  |  | A
| 26 |  | Our DH |  |  | Lack of project management resources are hindering the programme lead in visualising a holistic delivery across the multiple workstreams, which could result in opportunities for success being missed. |  |  | A
| 27 |  | Our DH |  |  | The Departmental culture may hinder progress within this project as a result of the organisation viewing IT technology as a solution to problems, rather than as an enabler for the organisation to perform more effectively. |  |  | A
| 28 |  | Our DH |  |  | Internal and Cross Departmental lines of reporting are focusing resources away from key tasks, which could ultimately hinder delivery. |  |  | A
| 29 |  | Our DH |  |  | Lack of project management resources are hindering the programme lead in visualising a holistic delivery across the multiple workstreams which could result in opportunities for success being missed. In addition the project is heavily reliant on volunteers; a key individual who planed how best to engage and support volunteers has recently left the organisation, this leaves a significant gap and risks a loss of support from volunteers. |  |  | A
| 1 | 2015-11-17 |  | Trust Wide | Income and expenditure deficit adverse to plan | Failure in statutory duty Liquidity TDA/DH Escalation Adverse public image NHS System impact | 5 | 4 | R | DoF | Control totals DH loan application Working capital facility Working capital strategy CCG and TDA escalation LTFM and financial strategy | 3 | 4 | A/R
| 2 | 2015-11-17 |  | Trust Wide | Inadequate staffing levels resulting in high levels of agency usage and associated costs | High levels of nursing and medical vacancies Insufficient workforce plans Lack of available qualified staff Potential impact on patient experience Potential to result in breach of CQC conditions of registration Capacity within corporate departments Impact of absence of DoF and Dep Dir Fin Vacancy | 5 | 4 | R | Dir of HR and OD | Advance preparation of rotas Overseas recruitment Workforce data reported monthly to Trust Board Plan to reduce bed numbers Use of bank and agency Investment in staffing | 3 | 3 | A
| 3 | 2015-11-17 |  | Trust Wide | Strategic change does not progress at a pace to address the sustainability of services | • Non delivery/delay of Clinical Strategy • Failure to modernise and deliver the digital strategy • System capacity pressures not addressed | 5 | 5 | R | Medical Director | Clinical Strategy Implementation Group Stakeholder board LHAC Lincolnshire Improvement Board | 4 | 4 | R
| 4 | 2015-11-17 |  | Trust Wide | Quality and safety compromised by pressure on capacity | •Increased risk of avoidable harm • Failure to comply with hygiene code • Capability to manage urgent patient flow on Pilgrim site Winter pressures | 5 | 5 | R | Director of Nursing/ Chief Operating Officer | Winter plan Monthly nurse staffing report Safety Quality Dashboard Safety Thermometer | 4 | 5 | R
| 5 | 2015-11-17 |  | Trust Wide | Harm or regulatory action resulting from inadequately maintained and obsolete infrastructure | • Inability to adequately comply with CQC and other regulators such as HSE with regards to statutory legal requirements concerning the safety of buildings and infrastructure leading to breach in legal compliance and risk of prosecution. • Risk of significant failure of services leading to prolonged loss of clinical facilities because of infrastructure failure such as power/ heating/ water supply etc. • Reduced assurance concerning the safety of occupants of premises. | 4 | 4 | R | Dir of Estates and Facilities | Development and deployment of estates investment plans for infrastructure investment. Development and deplyment of adequate cross-disciplinary maintenanance programmes. Appointment of Authorising Engineering services and associated governance and assurance actions following service review. Estates Workforce Review and adoption of revised work programmes. Ensure adequate numbers of estates staff are available and correctly trained and qualified to deliver a safe and suitable healthcare environment. | 3 | 4 | A/R |  | Mitigations require development and adoption to alter the risk grading, therefore the risk remains 16.
Open
Closed
[6 empty] | Open |  |  | A | G |  |  | 1 |  |  |  | Closed - Trans to Issue
[6 empty] | Closed |  |  | A/G | A/G |  |  | 2
[9 empty] | A/R | A |  |  | 3
[9 empty] | G | A/R |  |  | 4
[9 empty] | R | R |  |  | 5
A
A/R
R
R
R
A
A
A/R
R
R
A/G
A
A
A/R
A/R
G
A/G
A/G
A
A
G
G
G
G
G
Catastrophic-5
Major - 4
Moderate - 3
Minor - 2
Negligible- 1
1
Rare
2 Unlikely
3
Possible
4 Likely
5
Almost Certain
Likelihood
Impact
Overall Risk Rating
G

## RAGs (hidden)
A/R
A/G
RED
GRN
Amber
m