## U&E CARE (hidden)
Service / Initiative : URGENT AND EMERGENCY CARE FOR SOUTH EAST ESSEX
Objective | Deliverable |  | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
INFLOW Acute frailty service / unit will treat all older adult patients in a specialist unit to avoid unnecessary admissions and length of stay within our local hospital | GP referral to AFU | Target
Actual
| Pull patients from ED | Target
Actual
| Pull patients from the wards | Target
Actual
INFLOW Consultant connect | Avoid unnecessary attendances to A&E | Target
Actual
| Management of frequent flyers | Target
Actual
INFLOW Hospice care homes service | Supporting patients and families at home with inreach service | Target
Actual
| ADD | Target
Actual
INFLOW IRS team to be present at the A&E to reduce the transfer patients to this service avoiding uncessary admission | ADD | Target
Actual
| ADD | Target
Actual
Objective | Deliverable |  | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
FLOW Overall management and governance to ensure delivery of the agreed performance trajectory |  | Timescale
Timescale
Timescale
Timescale
Timescale
FLOW Implement Red + GREEN initiative to all wards at BTUH to provide a tool to actively manage patient care and meet agreed length of stay | Implement R+G day process to all…. | Target
Actual
| Reduce the number of stranded patients | Target
Actual
| Meet agreed length of stay | Target
Actual
FLOW Implement SAFER bundle in all wards at BTUH to effectively manage patient care and meet agreed length of stay | Implement SAFER bundle across all wards | Target
Actual
| Discharge patients on the agree EDD | Target
Actual
| Reduce length of stay | Target
Actual
FLOW Increase the number of patients treated in the Ambulatory Care to support the reduction in length of stay | Admission avoidance patients | Target
Actual
Target
Actual
Target
Actual
FLOW Increase the number of patients treated by the Acute Frailty Service to support reduced length of stay | Admission avoidance patients | Target
Actual
Target
Actual
Target
Actual
FLOW Develop the plan for the BTUH 'emergency village' | Admission avoidance patients | Timescale
Timescale
Timescale
FLOW Complete a review of the site bed model and patient pathways to support effective and productive flow - 'right patient - right place' | Reduction in the use of escalation beds | Target
Actual
| Agree the model and criteria for shared / off-site beds | Target
Target
Actual
Objective | Deliverable |  | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
OUTFLOW Implement the Discharge to Assess model | DTOC | Target
Actual
| Reduce the number of readmissions | Target
Actual
Target
Actual
OUTFLOW Weekend discharge team at BTUH to ensure that discharges are maintained over the full 7 day |  | Target
Actual
Target
Actual
| Meet agree length of stay | Target
Actual
OUTFLOW Integrated Care | ADD | Target
Actual
| ADD | Target
Actual

## Content page
The United Lincolnshire Hospitals NHS Trust Urgent & Emergency Care Recovery and Transformation Programme
CONTENT
Section 1
ULHT service model for urgent, emergency and ambulatory care
Model 'shape' at Lincoln Hospital
Model 'shape' at Pilgrim Boston Hospital
Section 2
Governance structure for delivery of the recovery and transformation programme
Governance structure of the organisational leadership and management
Section 6
Evidence
1. Emergency department
2. Assessment function
3. Site management
4. Inpatient and ward processes
5. Discharge and partnership working
Version Control.
This document is subject to version control.
All versions of the plan will be distributed as read only documents.
Project PMO via the Programme Lead is responsible for updating the plan and maintaining version control.
The plan will be version numbered and the title of the plan will include the latest revision date.
All requests for ammendments plan should be sent to Sarah.Hall68@nhs.net

## Model - ULHT
Urgent and Emergency Care Model - Overarching for ULHT

## Model - LCH site
Urgent and Emergency Care Model - LCH Site

## Model - PBH site
Urgent and Emergency Care Model - PBH Site

## Programme Structure
| Program Senior Responsible Officer (SRO) Clare Culpin, MD Division of Medicine |  |  |  | Roles and Responsibilities Programme Steering Group (PSG) Ensures various elements of the plan are reviewed, challenged and approved Receives and reviews work stream delivery reports and Programme risks and mitigations Identifies appropriate support for milestones that are off plan to ensure pace is maintained Considers dependencies across the work streams and resolves any inter programme issues or conflicts SROs Accountable to the PSG for delivery and assurance of the work streams Responsible for production of and changes to the work stream plan in partnership with the task and finish group(TFG) and action owners Responsible for convening the TFG and holding it to account for delivery action owners Responsible for identifying risks to delivery and agreeing support as required PMO/Improvement team Accountable to Senior SRO for providing support, guidance and assurance to the Programme/ Work streams and where appropriate delivery of actions Providing Strategic overview across work streams Informatics Accountable to PSG for agreeing metrics/improvement trajectories in partnership with the work streams, producing the programme dashboard and collating data which supports the monitoring of progress against agreed trajectories
1. Emergency Department Clare Culpin, Dr Megan Ryan & Tracey Wall | 2. Assessment Function Alistair Nelson, Dr Pavlos Zaferiris & Deborah Birch | 3. Site management Jamie Hodgkins, Dr Glen Spencer & Ward Sister tba | 4. Inpatient/Ward Process David Cleave, Clinical and Nursing Lead tba | 5. Discharge & Partnerships Michelle Harris, Clinical and Nursing Lead tba
Task & Finish Group Dr Dan Boden Tracy Bell Maxine Skinner Dr Hesham Turki Mandy Charles | Task & Finish Group Wendy Rojas Sofia Zubiaga SEAU Lead tbc Paed Lead tbc Milind Rao - Surg Laura Perrin-Brown Dr Lucy Daniels | Task & Finish Group Mandy Charles ECIST SAFER Lead tbc Michelle Harris Cheryl Thomson David O'Carroll | Task & Finish Group Bridy Clark Linda Keddie Glen Spencer Dan Boden or Angela Bullivant - ECIST Lead Michelle Harris | Task & Finish Group Haley Parkin Cheryl Thomson Social Worker tbc Clare Carr Katie Sayles Emma Wild Therapy Lead tba
PROJECT PMO
COMMUNICATION AND ENGAGEMENT STRATEGY - Lead Zoe Leahy
MEASUREMENT STRATEGY/DASH BOARD DEVELOPMENT - Lead Shaun Craig

## Project Approach
Project Vision and Objectives The Emergency Care Improvement Programme aims to prove high quality, timely, accessible and safe emergency care to patients, appropriate to their assessed needs, across organisation The Programme is designed to make enhancements to our emergency care services and pathways such that they: Deliver improved patient experience, safety and outcomes Benchmark positively against nationally agreed standards and metrics Reflect current best practice and evidence base Improve staff satisfaction, recruitment and retention Work in partnership with services delivered by partner agencies such that patients receive streamlined and timely care Represent value for money and best use of resources Key areas for change are: Emergency Departments Assessment Functions Site Management Wards and inpatient areas Discharge and Partnerships | Project Methodology Project methdology will align with QSIR. Awaiting Trust Methodology document from the 2021 project team.
Benefit Realisation Improved performance against nationally and locally agreed metrics VIA Programme Dashboard Improved performance against locally agreed quality metrics VIA Programme Dashboard Improved patient/carer satisfaction VIA F&FT Improved staff satisfaction VIA Staff survey, Local focus groups and questionnaires Improved patient safety and outcomes VIA Incident reporting system and learning outcomes/Programme Dashboard | Sustaining change post programme completion Celebrate success via agreed communication channels Ensure all changes to practice are embedded within the Emergency Care Standard Operating Procedures (SOPs), including agreed metrics/performance measures, accountability and training/induction for new starters Embed utilisation of the Emergency Care Dashboard in business as usual - such that data continues to be systematically collected, analysed at departmental, divisional and organisational level and any deterioration in performance can be identified and rectified. Establish clear accountability for data review and oversight Develop and implement contingency plans for specific changes to performance to support rectification

## Governance and Monitoring BAU
Division of Medicine - Draft Governance Structure including Urgent and Emergency Care

## KPI (hidden)
INFLOW
Objective | Measurable outcome | Performance - Target/Actual | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01
Reduce ambulance handover delays in the ED | Achieved the upper quartile of national performance with no 2 hour or longer delays at LCH | Target | 2018-04-01: Zero 2 hour ambulance handover delays
|  | Actual | 72 | 74 | 55 | 70 | 18 | 58 | 48 | 46
|  | Action | 2018-05-01: Revise the SOP for handover procedure and include a RCA of all cases that have breached the 2 hour delay; 2018-06-01: Include in the flow / capacity policy the escalation procedure for ambulance handover delays; 2018-09-01: Implement Early Intervention Vehicle
| Achieved the upper quartile of national performance with no 2 hour or longer delays at PBH | Target | 2018-04-01: Zero 2 hour ambulance handover delays
|  | Actual | 100 | 26 | 20 | 47 | 20 | 25 | 28 | 40
|  | Action | 2018-04-01: Introduce the role of the pre-hospital practitioners to triage patients on arrival to the ED. Agree a SOP for the role; 2018-05-01: Revise the SOP for handover procedure and include a RCA of all cases that have breached the 2 hour delay; 2018-06-01: Include in the flow / capacity policy the escalation procedure for ambulance handover delays; 2018-09-01: Include the monitoring and performance of ambulance handovers into the revised daily dashboard
| Achieved the upper quartile of national performance with no 2 hour or longer delays at GDH | Target | 2018-04-01: Zero 2 hour ambulance handover delays
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Action | 2018-09-01: Align the site policy and procedure with the wider trust
Deliver an effective GP streaming service | Appropriate patients have been effectively directed to the GP streaming service at LCH | Target | 2018-04-01: Q1 - 20% of all patients attending the ED will be streamed to the GP; 2018-07-01: Q2- 30% of all patients attending the ED will be streamed to the GP
|  | Actual | 13.02% | 17.06% | 13.69% | 13.69% | 14.64% | 12.16% | 12.6% | 25%
|  | Action | 2018-04-01: Introduce the role of GP streaming in the ED provided by community partners LCHS
| Appropriate patients have been effectively directed to the GP streaming service at PBH | Target | 2018-04-01: Q1 - 16% of all patients attending the ED will be streamed to the GP; 2018-07-01: Q2 - Increase to 25% of all patients attending the ED will be streamed to the GP
|  | Actual | 6.086% | 6.876% | 7.569% | 7.629% | 10.55% | 15.26% | 15.9% | 29%
|  | Action | 2018-04-01: Introduce the role of GP streaming in the ED provided by community partners LCHS; 2018-09-01: Introduce the new space for GP streaming to support more effective working; 2018-10-01: launch new model with all walk-in patients going through streaming at front desk
Improve time to Triage for patients, contributing to the achievement of the four hour standard trajectory | 100% of eligible nurses are trained to deliver triage at LCH. | Target | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses
|  | Actual | 2018-10-01: 81.3%; 2018-11-01: 100%
|  |  | Undertake a training needs analysis, develop a training plan , produce a trajectory | There is a monitoring process in place to manage triage performance | All staff are eligible staff are trained in triage | Spot-checks undertaken by lead ACP to give assurance that Triage standards are maintained . |  |  | The rota provides 1 triage nurse 24/7 and an additional nurse between 10 -10
| 100% of eligible nurses are trained to deliver triage at PH. | Target | 70% | 80% | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses
|  | Actual | 64% | 74% | 80% | 83% | 91% | 77% | 89% | 86%
|  |  | Undertake a training needs analysis, develop a training plan , produce a trajectory | There is a monitoring process in place to manage triage performance | All staff are eligible staff are trained in triage | Spot-checks undertaken by lead ACP to give assurance that Triage standards are maintained . |  |  | The rota provides 1 triage nurse 24/7 and an additional nurse between 10 -10
| 100% of eligible nurses are trained to deliver triage at GH. | Target | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses | 100% of nurses
|  | Actual | 2018-10-01: 91%; 2018-11-01: 100%
|  |  | Undertake a training needs analysis, develop a training plan , produce a trajectory | There is a monitoring process in place to manage triage performance | All staff are eligible staff are trained in triage | Spot-checks undertaken by lead ACP to give assurance that Triage standards are maintained . |  |  | The rota provides 1 triage nurse 24/7 and an additional nurse between 10 -10
| patients are triaged within 15 minutes of arrival at LCH | Target | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
|  | Actual | 67.46% | 75.39% | 77.75% | 79.37% | 82.41% | 80.31% | 79.85% | 77.25%
[9 empty] | Process in place to ensure that all records of patient triage are completed | compliance with Triage monitored and recorded in 2 x daily assurance report. Individual Nurse performance monitored and issues addressed
| patients are triaged within 15 minutes of arrival at PH | Target | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
|  | Actual | 47.33% | 53.25% | 56.52% | 47.85% | 45.74% | 50.2% | 58.87% | 57%
[9 empty] | Process in place to ensure that all records of patient triage are completed | compliance with Triage monitored and recorded in 2 x daily assurance report. Individual Nurse performance monitored and issues addressed
| patients are triaged within 15 minutes of arrival at GH | Target | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85% | 85%
|  | Actual | 60.17% | 58.12% | 64.88% | 63.05% | 61.34% | 65.69% | 64.6% | 71.19%
[9 empty] | Process in place to ensure that all records of patient triage are completed | compliance with Triage monitored and recorded in 2 x daily assurance report. Individual Nurse performance monitored and issues addressed
Improve time for RAIT for all patients, contributing to the achievement of the four hour standard trajectory | 100% of patients go through RAIT within 30 minutes of arrival in the ED at LH | Target | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actual | bar: 2018-04-01 to 2018-11-01
|  |  | All appropriate staff are competent to undertake RAIT | The rota provides appropriate numbers of staff to complete the RAIT process | There is a monitoring process is place to ensure effective RAIT is taking place |  |  |  | Revision of monitoring process to ensure effective RAIT is taking place | ECIST supporting review of RAIT attainment
| 100% of patients go through RAIT within 30 minutes of arrival in the ED at PH | Target | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Actual | bar: 2018-04-01 to 2018-11-01
|  |  | All appropriate staff are competent to undertake RAIT | The rota provides appropriate numbers of staff to complete the RAIT process | There is a monitoring process is place to ensure effective RAIT is taking place |  |  |  | Revision of monitoring process to ensure effective RAIT is taking place | ECIST supporting review of RAIT attainment
| 100% of patients go through RAIT within 30 minutes of arrival in the ED at GDH | Target
Actual | bar: 2018-04-01 to 2018-11-01
|  |  | All appropriate staff are competent to undertake RAIT | The rota provides appropriate numbers of staff to complete the RAIT process | There is a monitoring process is place to ensure effective RAIT is taking place |  |  |  | Revision of monitoring process to ensure effective RAIT is taking place | ECIST supporting review of RAIT attainment
To increase the number of urgent, emergency and ambulatory care pathways to avoid unnecessary attendance at ED and improve the patients outcome and experience - Deliver an effective Fractured Neck of Femur pathway | Deliver the direct to care fractured neck of femur patient pathway at LCH | Target | 2018-04-01: Zero avoidable four hour transit time breaches for patients with a #NoF; 2018-12-01: Patients with a diagnosis of #NoF are directly admitted to a bed within 2 hours of arriving in ED
Actual
|  | Action | 2018-07-01: Review the pathway with key stakeholders; 2018-08-01: Approve and agree the pathway through relevant governance groups, including operational implementation plan; 2018-09-01: Prepare all clinical and operational teams for the implementation and launch on 1st October 2018
| Deliver the direct to care fractured neck of femur patient pathway at PBH | Target | 2018-04-01: Zero avoidable four hour transit time breaches for patients with a #NoF; 2018-12-01: Patients with a diagnosis of #NoF are directly admitted to a bed within 2 hours of arriving in ED
Actual
|  | Action | 2018-07-01: Review the pathway with key stakeholders; 2018-08-01: Approve and agree the pathway through relevant governance groups, including operational implementation plan; 2018-09-01: Prepare all clinical and operational teams for the implementation and launch on 30th October 2018
To increase the number of urgent, emergency and ambulatory care pathways to avoid unnecessary attendance at ED and improve the patients outcome and experience - Deliver an effective direct access stroke care pathway | Zero four hour transit time breaches for FAST positive / stroke patients at LCH | Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual
|  | Action | 2018-08-01: Ensure with the introduction of the bed model and revised capacity management processes that there is always a ring fenced stroke care bed
| Zero four hour transit time breaches for FAST positive / stroke patients at PBH | Target | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual
|  | Action | 2018-08-01: stoke pathway review
Improve the patients and staff experience of the ED and achieve the four hour transit time trajectory - Deliver an effective minor injury and minor illness pathway | There is an effective minor injury and minor illness streaming and pathway which is staffed and led by experienced clinicians and delivers the non-admitted four hour transit time standard at LCH | Target | 2018-04-01: Non-admitted performance >98% (all types)
Actual
|  | Action | 2018-04-01: Understand reasons for minors breaches and how the majors and minors areas are utilised to deliver care; 2018-07-01: Review and agree the model for urgent, emergency and ambulatory care services at ULH, include the model for Minor Injuries and align with the GP streaming service; 2018-08-01: Right size and shape the service capacity; 2018-09-01: Agree and ratify the SOP for the service and engage staff in a table top exercise; 2018-10-01: Launch the new pathways and SOP and use the 're-set' approach to ensure an effective starting point. Support with strong operational leadership
| There is an effective minor injury and minor illness pathway which is staffed and led by experienced clinicians and delivers the non-admitted four hour transit time standard at PBH | Target | 2018-04-01: Non-admitted performance >98% (all types)
Actual
|  | Action | 2018-04-01: Understand reasons for minors breaches and how the majors and minors areas are utilised to deliver care; 2018-07-01: Review and agree the model for urgent, emergency and ambulatory care services at ULH, include the model for Minor Injuries and align with the GP streaming service; 2018-08-01: Right size and shape the service capacity; 2018-09-01: Agree and ratify the SOP for the service and engage staff in a table top exercise; 2018-10-01: Launch the new pathways and SOP and use the 're-set' approach to ensure an effective starting point. Support with strong operational leadership
| There is an effective minor injury and minor illness pathway which is staffed and led by experienced clinicians and delivers the non-admitted four hour transit time standard at GDH | Target | 2018-04-01: Non-admitted performance >98% (all types)
Actual
|  | Action | 2018-04-01: Understand reasons for minors breaches and how the majors and minors areas are utilised to deliver care; 2018-07-01: Review and agree the model for urgent, emergency and ambulatory care services at ULH, include the model for Minor Injuries and align with the GP streaming service; 2018-08-01: Right size and shape the service capacity; 2018-09-01: Agree and ratify the SOP for the service and engage staff in a table top exercise; 2018-10-01: Launch the new pathways and SOP and use the 're-set' approach to ensure an effective starting point. Support with strong operational leadership
Improve the patients and staff experience of the ED and achieve the four hour transit time trajectory - model and infrastructure | The model for urgent, emergency and ambulatory care at ULH meets the profile of the demand | Action | 2018-07-01: Ensure the multidisciplinary team staffing model meets the profile of demand by reviewing and approving the staff rosters; 2018-08-01: Review the Trust bed model and include ambulatory care capacity requirements; 2018-09-01: Agree for each ward the following: beds / trolleys for each ward LOS for each ward Number of DTOC and stranded patients for each ward Discharge levels for each ward
| There is a reduction of the conversion rate to admission (for further development with ECIST) | Target | Conversion rate of 25% | Conversion rate of 25% | Conversion rate of 25% | Conversion rate of 25% | Conversion rate of 25% | Conversion rate of 25% | Conversion rate 27% | Conversion rate 27%
|  | Actual | 26% | 26% | 25% | 25% | 26% | 27% | 28.5% | 28.71%
|  | Action | 2018-05-01: Reduce conversion rate - target 25% performance in line with benchmarking/Model Hospital; 2018-07-01: Interprofessional standards are up to date and agreed. Monitoring of adherence is in place.; 2018-08-01: Specialty responsiveness is monitored and included in the performance dashboards; 2018-10-01: (weekly average)
| The environment is conducive to delivering safe, effective care and there are no outstanding estates work that impedes care. | Action | 2018-06-01: All outstanding estates work is identified and there is a plan to address. Delivery is monitored weekly and shared with the ED recovery group.; 2018-07-01: There is a clear delivery plan for the estates work at PBH which is being monitored weekly.
Improve the patients and staff experience of the ED and achieve the four hour transit time trajectory - safety and quality | There are effective safety huddles are held in the ED every 2 hours (24/7) led by the clinical in charge of the shift to prioritise patient care, sustain team working and align with safety escalation procedures at ULH | Target | 2018-08-01: Audit of huddles
Actual
|  | Action | 2018-08-01: Agree the standard, structure and process for safety huddles in ED based on best practice with all key stakeholders.; 2018-09-01: Implement using the PDSA cycle and evaluate; 2018-10-01: Agree the final practice model for safety huddles and continue to undertake them every 2 hours in the ED, inviting ambulatory care colleagues to identify patients for transfer
| Insert CQC items | Target
Actual
Action
Improve the patients and staff experience of the ED and achieve the four hour transit time trajectory - Staff skills and competency | Ensure the Medical workforce model meets the profile of demand by reviewing and approving the staff rosters | Target | 2018-04-01: 95% of all medical staff working in the ED are trained in PILS
Actual LCH
Actual PBH
Actual GDH
|  | Action | 2018-07-01: Medical workforce review to deliver care across all sites. Modelling the leadership and management of the team.; 2018-08-01: Develop the roster for the shared medical workforce. Have a strong plan for the recruitment into vacant posts.; 2018-09-01: Monitor & Audit responsiveness of speciality assessment against professional standards; 2018-10-01: Commence the shared roster; 2018-11-01: Productivity is monitored at individual level
| Ensure the Nursing and Professional workforce model meets the profile of demand by reviewing and approving the staff rosters | Target | 2018-04-01: 95% of all nursing staff working in the ED have completed training in Triage and Paediatric emergency care competencies
Actual
|  | Action | 2018-07-01: Nursing and Professions workforce review to deliver care across all sites. Modelling the leadership and management of the team.; 2018-08-01: Develop the roster for the shared nursing and professions workforce. Have a strong plan for the recruitment into vacant posts.; 2018-09-01: Consult and agree new roster. Ensure there is a training and support programme to enable practitioners to deliver safe, effective care.
Target
Actual
|  | Action | 2018-05-01: Audit responsiveness of speciality assessment against professional standards
To increase the number of patients seen within 30 minutes following referral to speciality | 100% of patients requiring a speciality review are seen within 30 minutes of the request at LH | Target
Actual
[6 empty] | Sop developed for referral to speciality | Sop approved at CMB |  | There is a monitoring process to give assurance that patients are seen within 30 mins
| 100% of patients requiring a speciality review are seen within 30 minutes of the request at PH | Target
Actual
[6 empty] | Sop developed for referral to speciality | Sop approved at CMB |  | There is a monitoring process to give assurance that patients are seen within 30 mins
| 100% of patients requiring a speciality review are seen within 30 minutes of the request at GDH | Target
Actual
[6 empty] | Sop developed for referral to speciality | Sop approved at CMB |  | There is a monitoring process to give assurance that patients are seen within 30 mins
Patients will feel safe, secure and supported | Patients are streamed to the most appropriate service to meet their health care needs. | Action | 2018-09-01: SOP for streaming patients for the most appropriate service to meet their health care needs -LCHS
A/E staff have completed mandatory and essential clinical training | 90% of identified staff are compliant with blood transfusion competency and electronic blood tracking systems assessments. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| 90% of identified staff are compliant with Sepsis Training. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| 90% of identified staff are compliant with the Safe use of Insulin Training. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| 90% of identified staff who are required have attended BLS. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| The trust must ensure all frontline clinical staff are trained in the key skill fit testing of respiratory protective equipment face pieces, (90%) | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| All nursing staff have received training for CBRN (90%) | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| 90% Staff mandatory training is compliant for Infection Prevention for that area. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
| Staff have completed the Trust Falls workbook. | Target | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Actual
|  |  | BLUE | Delivered
|  |  | GREEN | On target to deliver by the due date
|  |  | AMBER | Behind schedule but recovery plan in place
|  |  | RED | Behind schedule no recovery plan in place
Note on L26: Wilding Kim (ULHT): source MS
Note on L38: Wilding Kim (ULHT): not updated

## 1 ED Evidence (hidden)
Trial Metrics Template (ULHT Version) - 2018-10-22 to 28th October.pptx
Response request: 01/11/18 Emma Coulson, General Manager Urgent and Emergency Care
Emergency Department Scoping Questionnaire 2018 FINAL (002).docx
“The Board have asked for an update on actions taken in relation to medical staff since the incidents that were identified last week. I am aware that you have written an action plan, could you provide me with an update in terms of medical staff please?”
AE Monthly Perf Tracker 181101.xlsx
Incidents regarding medical staffing following The Emergency Department Accreditation as taken from the team brief documents 26/10/18
1.1 Insufficient numbers of staff to care for children
1 member of Medical staff had no valid DBS and some medical staff not up to date with paediatric life support
Actions
Incidents to report:
Medic with no DBS
Level of staff having EPALS training
Immediate actions
DBS needs to be resolved, or removal of staff from duty until DBS obtained, or appropriate risk assessment and supervision. ED leadership team
Action by the Clinical Business Unit:
Checked that the doctor was compliant with DBS
Process embedded previously around the compliance of agency as below, this is checked and monitored.
The doctor below showing red for references using this monitoring was then discussed with HOLT and is now compliant.
No doctor should be recommended by HOLT unless fully compliant, any concerns issues are discussed and raised with Clare Mundy- Holt Contract Manager, Human Resources
Following the CQC review the following process was also implemented and embedded
Support the medical staff with EPALS training and monitor compliance
Currently all consultants are compliant
There are 2 middle grades that are not compliant, 1 on the bank booked for training in December the other is substantive and also booked in December
The evidence for the training is filed and maintained in the department by the rota coordinator team and overseen by the operational service manager.
To support with daily compliance the medical compliance and Paediatric training compliance was added to the daily temperature check as below
ED response - yesterday feedback.docx